## PROJECT DATA
Project ID | Project | Region | UNIQUE REGIONS | Project Manager | Start Date | End Date | MONTH | UNIQUE MONTH | REVENUE BY MONTH | Budget ₦M | ACTUAL COST BY MONTH | PROFIT BY MONTH | Actual Cost ₦M | Revenue ₦M | Planned Progress % | Actual Progress % | Labour Cost ₦M | Material Cost ₦M | Client Rating | Staff | PROFIT ₦M | PROFIT MARGIN | BUDGET VARIANCE (NM) | PROGRESS VARIANCE | COST EFFICIENCY | LABOUR COST % | MATERIAL COST % | PROJECT STATUS
P009 | Abuja Stadium | Abuja | Abuja | King | 2025-03-18 | 2026-02-15 | March | March | 1240 | 500 | 485 | 125 | 485 | 610 | 82 | 85 | 135 | 195 | 4.3 | 105 | 125 | 20.49% | 15 | 3 | 1.2577 | 27.84% | 40.21% | HEALTHY
P007 | Abuja Airport | Abuja | Lagos | Danladi | 2025-01-10 | 2025-12-20 | January | January | 955 | 450 | 430 | 110 | 430 | 540 | 98 | 96 | 120 | 175 | 4.8 | 90 | 110 | 20.37% | 20 | -2 | 1.2558 | 27.91% | 40.7% | ATTENTION
P014 | Lekki Towers | Lagos | Kano | Emeka | 2025-03-01 | 2026-02-15 | March | February | 695 | 420 | 400 | 110 | 400 | 510 | 85 | 88 | 110 | 165 | 4.5 | 82 | 110 | 21.57% | 20 | 3 | 1.275 | 27.5% | 41.25% | HEALTHY
P003 | VI Bridge | Lagos | Enugu | Okoro | 2025-03-20 | 2025-11-30 | March | April | 590 | 320 | 305 | 85 | 305 | 390 | 90 | 94 | 85 | 120 | 4.7 | 65 | 85 | 21.79% | 15 | 4 | 1.2787 | 27.87% | 39.34% | HEALTHY
P012 | Kano Hospital | Kano |  | Garba | 2025-02-25 | 2025-12-10 | February | May | 420 | 275 | 260 | 80 | 260 | 340 | 88 | 90 | 70 | 105 | 4.6 | 60 | 80 | 23.53% | 15 | 2 | 1.3077 | 26.92% | 40.38% | HEALTHY
P013 | Abuja Mall | Abuja |  | Ibrahim | 2025-04-10 | 2026-01-30 | April | June | 150 | 380 | 395 | 65 | 395 | 460 | 78 | 74 | 105 | 155 | 3.9 | 80 | 65 | 14.13% | -15 | -4 | 1.1646 | 26.58% | 39.24% | ATTENTION
P001 | Lekki Hospital | Lagos |  | Adewale | 2025-01-05 | 2025-12-20 | January |  |  | 180 |  |  | 165 | 220 | 95 | 92 | 48 | 62 | 4.5 | 42 | 55 | 25% | 15 | -3 | 1.3333 | 29.09% | 37.58% | ATTENTION
P005 | Enugu Estate | Enugu |  | Obi | 2025-04-08 | 2026-02-15 | April |  |  | 210 |  |  | 198 | 250 | 80 | 82 | 55 | 82 | 4.2 | 50 | 52 | 20.8% | 12 | 2 | 1.2626 | 27.78% | 41.41% | HEALTHY
P008 | Lekki Mall | Lagos |  | Udo | 2025-02-22 | 2026-01-30 | February |  |  | 170 |  |  | 160 | 210 | 88 | 91 | 42 | 65 | 4.6 | 38 | 50 | 23.81% | 10 | 3 | 1.3125 | 26.25% | 40.62% | HEALTHY
P015 | Enugu Road | Enugu |  | Chukwu | 2025-05-15 | 2025-11-30 | May |  |  | 130 |  |  | 118 | 165 | 95 | 97 | 32 | 45 | 4.7 | 28 | 47 | 28.48% | 12 | 2 | 1.3983 | 27.12% | 38.14% | HEALTHY
P010 | Enugu Hotel | Enugu |  | Paul | 2025-06-05 | 2026-04-20 | June |  |  | 150 |  |  | 142 | 185 | 70 | 72 | 38 | 55 | 4 | 35 | 43 | 23.24% | 8 | 2 | 1.3028 | 26.76% | 38.73% | HEALTHY
P006 | Ikeja Offices | Lagos |  | James | 2025-05-01 | 2026-03-30 | May |  |  | 290 |  |  | 310 | 350 | 75 | 68 | 92 | 128 | 3.8 | 72 | 40 | 11.43% | -20 | -7 | 1.129 | 29.68% | 41.29% | CRITICAL
P004 | Kano School | Kano |  | Bello | 2025-01-15 | 2025-10-25 | January |  |  | 95 |  |  | 88 | 120 | 100 | 98 | 24 | 35 | 4.4 | 30 | 32 | 26.67% | 7 | -2 | 1.3636 | 27.27% | 39.77% | ATTENTION
P011 | Lagos Estate | Lagos |  | Adeyemi | 2025-01-12 | 2025-11-15 | January |  |  | 230 |  |  | 245 | 275 | 92 | 86 | 65 | 100 | 4.1 | 55 | 30 | 10.91% | -15 | -6 | 1.1224 | 26.53% | 40.82% | CRITICAL
P002 | Abuja Highway | Abuja |  | Musa | 2025-02-12 | 2026-01-15 | February |  |  | 250 |  |  | 270 | 285 | 85 | 79 | 72 | 105 | 4.1 | 58 | 15 | 5.263% | -20 | -6 | 1.0556 | 26.67% | 38.89% | CRITICAL

## ANALYSIS
Project ID | DYNNAMIC CHART DATA |  | ITEMS | RESULTS | UNIQUE MONTH | REVENUE | ACTUAL COST | PROFIT | ITEMS | AMOUNT | Project | Actual Cost ₦M | Revenue ₦M | Staff | REGION | Revenue ₦M | Project | Over-Budget ₦M | Cumulative % | 80% | PERFORMANCE HEAT MAP
P001 | SELECTED PROJECT | DROP DOWN | TOTAL REVENUE (NM) | 4910 | March | 1240 | 485 | 125 | TOTAL REVENUE (NM) | 4910 | Abuja Stadium | 485 | 610 | 105 | Abuja | 1895 | Abuja Highway | 20 | 28.57% | 80% | REGION | Revenue ₦M | PROFIT ₦M | MARGIN | CLIENT RATING
P002 | PROJECT ID | P001 | TOTAL ACTUAL COST (NM) | 3971 | January | 955 | 430 | 110 | TOTAL ACTUAL COST (NM) | -3971 | Abuja Airport | 430 | 540 | 90 | Lagos | 1955 | Ikeja Offices | 20 | 57.14% | 80% | ABUJA | 1895 | 315 | 16.62% | 4.275
P003 | AMOUNT | ₦M | TOTAL PROFIT (NM) | 939 | February | 695 | 400 | 110 | TOTAL PROFIT (NM) | 939 | Lekki Towers | 400 | 510 | 82 | Kano | 460 | Lagos Estate | 15 | 78.57% | 80% | LAGOS | 1955 | 370 | 18.93% | 4.3667
P004 | REVENUE | 220 | AVERAGE PROFIT MARGIN | 19.83% | April | 590 | 305 | 85 |  |  | VI Bridge | 305 | 390 | 65 | Enugu | 600 | Abuja Mall | 15 | 100% | 80% | KANO | 460 | 112 | 24.35% | 4.5
P005 | ACTUAL COST | 165 | PROJECTS OVER BUDGET | 4 | May | 420 | 260 | 80 |  |  | Kano Hospital | 260 | 340 | 60 | [6 empty] | ENUGU | 600 | 142 | 23.67% | 4.3
P006 | PROFIT | 55 | AVERAGE CLIENT RATING | 4.3467 | June | 150 | 395 | 65 |  |  | Abuja Mall | 395 | 460 | 80
P007 | [10 empty] | Lekki Hospital | 165 | 220 | 42
P008 | [10 empty] | Enugu Estate | 198 | 250 | 50
P009 | [10 empty] | Lekki Mall | 160 | 210 | 38
P010 | [10 empty] | Enugu Road | 118 | 165 | 28
P011 | [10 empty] | Enugu Hotel | 142 | 185 | 35
P012 | [10 empty] | Ikeja Offices | 310 | 350 | 72
P013 | [10 empty] | Kano School | 88 | 120 | 30
P014 | [10 empty] | Abuja Stadium | 245 | 275 | 55
P015 | [10 empty] | Abuja Airport | 270 | 285 | 58

## DASHBOARD
DYNAMIC CHART
4910
TOTAL REVENUE
20%
AVERAGE PROFIT MARGIN
4
PROJECTS OVER BUDGET
939
TOTAL PROFIT
3971
TOTAL ACTUAL COST
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.